## Sheet1
Sr No | Details | Date | Status | Comment
1 | How we can track the status of the work ? i.e. provision must be there to have status of each task. i.e. Work in progress, Completed, On Hold, Pending. | 2020-02-21 | Done
2 | There must be provision to put comment related to respective status. | 2020-03-03 | Done
3 | Total working hours should be calculated automatically. | 2020-02-21 | Done
4 | We can keep provision of employee profile into the system. i.e. his or her joining date and some personal information. | 2020-03-04 | Done | Functionality is implemented
5 | We should keep provision for IN TIME and OUT TIME for each of the employee. | 2020-02-21 | Not Started
6 | There is Work Date in the system, however we can keep Work Completion Date into the system. | 2020-02-21 | Not Started
7 | We can include Leave management system in this portal. | 2020-03-05 | Done | Functionality is implemented
8 | On dashboard, we can higligh different events or important information about our organization. | 2020-02-21 | Not Started
9 | Clear should reload data to original, right now only filters cleared but data remains same | 2020-03-03 | Done | Sometimes it shows error once we clicked on SEARCH button.-Working fine from my end
10 | Task total hours are wrongly calculated | 2020-02-26 | Done
11 | Export shows all data 2 times. | 2020-03-03 | Done | From employee / admin login, export option is not working.-Export working now
12 | Sorting is not working in Start Time, End time | 2020-03-03 | Done | Done
13 | Add filter of Status in View timesheet | 2020-02-26 | Done
14 | Remove hyperlinked column name from exported data and keep simple text. | 2020-03-03 | Done | Have not checked as export option is not working-Export Working now
15 | Employee name is mandatory in filter, so I can not search entire project’s time as admin | 2020-02-26 | Done
16 | Add Email id for employees | 2020-03-03 | Done | In grid details, kindly add column for email id.-Added
17 | Forget password -> send mail | 2020-03-03 | Done | It shows error message once we entered email id in forgot password.-Email must be in database else message wil be displayed.
18 | Send mail on employee create with their password and then they should be able to change it | 2020-02-26 | Pending | Email not received
19 | Password should be encrypted in database | 2020-03-03 | Done | I don’t have access of database. Please check from your side.-It is encrypted
20 | Same number employee add-> should show message number already exists | 2020-03-03 | Done | Message is not display regarding same employee instead ADD button gets disabled.
Message should also display on screen.-"Employee Exists" is displayed
21 | From admin login, kindly add employee name column and total hour ( with respect to task ) in grid. So when we export timesheet details into excel, it will be easier for us to check information based on each employee. | 2020-03-03 | Done
22 | Once we clicked on ADD button after entering respective employee details, ADD button got disabled. This should get enabled once we go to add employee page to add new employee details. | 2020-03-05 | Done
23 | Message should display with respect to added employee once we clicekd on ADD button. | 2020-03-03 | Done
Message should be "Employee added successfully".